# Moffat Bay Marina - Group Task List & Work Estimations

Each page is broken into Front End, Back End, and Database needs. Estimated hours are approximate - see citations below.

| Task | Description | Estimated Hours | Due Date |
| --- | --- | --- | --- |
| MODULE 1 - Project Setup & Requirements Gathering (due Aug 16) - DONE |  |  |  |
| Requirements Gathering | Draft data requirements, user personas, and user stories for the TDD | 6 hrs | Aug 16 (Done) |
| Project Setup | Confirm Marina project, set up GitHub repo, shared MySQL environment, comms channel | 4 hrs | Aug 16 (Done) |
| MODULE 2 - Prototype (due Aug 23) |  |  |  |
| Page Prototypes | Functional prototype for all 9 pages (Landing, About Us, Contact Us, Wait List Lookup, Registration, Login, Slip Reservation, Reservation Summary, Look Up Reservation) | 9 hrs | Aug 23 |
| Landing Page Mockup | Realistic mockup (color, layout, font) of the Landing page | 3 hrs | Aug 23 |
| MODULE 3 - ERD (due Aug 30) - DATABASE |  |  |  |
| Entity Relationship Diagram | Design the ERD covering customers, slips, reservations, and wait list, and how they relate | 6 hrs | Aug 30 |
| MODULE 4 - Database Development, Sprint 1 (due Aug 30) - DATABASE |  |  |  |
| Database Schema | Build the MySQL schema from the ERD (customers, slips, reservations, wait list tables) | 6 hrs | Aug 30 |
| Slip Inventory | Load slip inventory by size category (26 ft, 40 ft, 50 ft) based on the marina map | 2 hrs | Aug 30 |
| Shared Data Access Functions | Build shared functions so every page has a consistent way to read/write the database | 7 hrs | Aug 30 |
| Password Hashing | Research and implement password hashing approach (cited source) | 4 hrs | Aug 30 |
| MODULE 5 - Web Dev 1, Sprint 2 Begins (due Sep 6) |  |  |  |
| Landing Page - Front End | HTML/CSS build | 3 hrs | Sep 6 |
| Landing Page - Back End | Any dynamic content | 2 hrs | Sep 6 |
| Landing Page - Database | None - static content | - | Sep 6 |
| Login Page - Front End | Username/password form | 2 hrs | Sep 6 |
| Login Page - Back End | Check credentials, hash check, start session | 4 hrs | Sep 6 |
| Login Page - Database | Reads customers table (username, password hash) | - | Sep 6 |
| Registration Page - Front End | Registration form | 2 hrs | Sep 6 |
| Registration Page - Back End | Create customer record, validate email format, hash password | 4 hrs | Sep 6 |
| Registration Page - Database | Writes to customers table (new row, unique CustomerID, hashed password) | - | Sep 6 |
| Module 5 Test Plan | 6 functional tests (2 per page) using TestPlanTemplate.docx, run and document with screenshots | 3 hrs | Sep 6 |
| MODULES 6 & 7 - Web Dev 2 & 3, Sprint 2 Continues (due Sep 13) |  |  |  |
| Slip Reservation Page - Front End | Reservation form | 3 hrs | Sep 13 |
| Slip Reservation Page - Back End | Boat-length-to-slip-size matching, availability check | 5 hrs | Sep 13 |
| Slip Reservation Page - Database | Reads slips (availability by size), writes reservations | - | Sep 13 |
| About Us Page - Front End | HTML/CSS build | 2 hrs | Sep 13 |
| About Us Page - Back End | Any dynamic content | 1 hr | Sep 13 |
| About Us Page - Database | None - static content | - | Sep 13 |
| Reservation Summary Page - Front End | Summary display | 2 hrs | Sep 13 |
| Reservation Summary Page - Back End | Pull reservation + slip details for display | 3 hrs | Sep 13 |
| Reservation Summary Page - Database | Reads reservations, slips, customers | - | Sep 13 |
| Module 7 Test Plan | 4 functional tests (2 per page) | 2 hrs | Sep 13 |
| Scrum 2 Discussion | Initial post plus 3 peer responses (per person) | 1 hr/person | Sep 13 |
| MODULE 8 - Web Dev 4, Sprint 3 Begins (due Sep 20) |  |  |  |
| Contact Us Page - Front End | HTML/CSS build | 2 hrs | Sep 20 |
| Contact Us Page - Back End | Any dynamic content | 1 hr | Sep 20 |
| Contact Us Page - Database | None - static content (unless a stored contact form is added later) | - | Sep 20 |
| Look Up Reservation Page - Front End | Lookup form | 2 hrs | Sep 20 |
| Look Up Reservation Page - Back End | Query reservation by ID/customer | 3 hrs | Sep 20 |
| Look Up Reservation Page - Database | Reads reservations | - | Sep 20 |
| Module 8 Test Plan | 4 functional tests (2 per page) | 2 hrs | Sep 20 |
| Scrum 3 Discussion | Initial post plus 3 peer responses (per person) | 1 hr/person | Sep 20 |
| MODULE 9 - Web Dev 5, Sprint 3 Wraps Up (due Sep 27) |  |  |  |
| Wait List Lookup Page - Front End | Wait list display | 2 hrs | Sep 27 |
| Wait List Lookup Page - Back End | Wait-list logic when a slip size is full | 4 hrs | Sep 27 |
| Wait List Lookup Page - Database | Reads/writes wait_list, reads slips | - | Sep 27 |
| Module 9 Test Plan | 2 functional tests | 1 hr | Sep 27 |
| MODULE 10 - QA & Peer Review (due Oct 4) |  |  |  |
| QA Presentation | Team intro, prototypes, ERD, 5+ tests and results, lessons learned | 4 hrs | Oct 4 |
| Screen Capture Walkthrough | Narrated recording walking through every page of the site | 3 hrs | Oct 4 |
| MODULE 11 - QA Testing & Delivery (due Oct 11) |  |  |  |
| Peer Critiques | 2 critiques of other teams, 150+ words each, 2 strengths/2 improvements | 2 hrs/person | Oct 11 |
| Peer Feedback Fixes | Fix issues raised in peer feedback across pages/database | 5-8 hrs | Oct 11 |
| Changes Write-Up | Document the changes made based on feedback | 2 hrs | Oct 11 |
| Final Submission | Zip and submit the final project | 1 hr | Oct 11 |

## How These Estimates Were Generated

We started with two numbers we found while researching typical web project timelines: about 40 hours for planning and design, and roughly 5 hours to build each page. For the login page, we used a starting point of 1 to 3 hours for a basic username and password check. From there, we adjusted each task up or down by hand. A page like Slip Reservation, which has to match a boat's length to an open slip, took more time than something like the About Us page. It's worth knowing that both of these numbers came from articles written to help price out client projects, not from a formal study of how long development actually takes. So think of them as a solid starting point, not a guarantee.

## References

Martin, M. (2025, February 12). How much does it cost to develop a website? DesignRush. https://www.designrush.com/agency/web-development-companies/trends/cost-of-web-development

NS804. (2019, June 4). How much does it cost to implement login capabilities? https://www.ns804.com/blog/how-much-does-it-cost-to-implement-login-capabilities/